WikiWalks – Iteration Plan 2

# Key milestones

|  |  |
| --- | --- |
| Milestone | Date |
| Iteration start | 2020-03-30 |
| Mid-iteration meeting | 2020-04-06 |
| Iteration stop | 2020-04-12 |

# High-level objectives

1. Evaluate and document proposed architectures and platforms
2. Create initial design for critical core use case
3. Create technology competency demonstrators
4. Create initial master test plan
5. Create initial master project plan

# Evaluation criteria

1. Proposed architectures are finalised and well-documented
2. Critical core use case is properly designed
3. Technology competency demonstrators are functional
4. Initial master test plan is complete and detailed
5. Initial master project plan is complete and detailed

# Work item assignments

The following work items will be addressed in this iteration:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Work Item ID | Name or Description Key Words | Outcome | State | Assignee | Estimated Hours | Hours Worked | Hours Remaining |
| 1 | Evaluate and document architectures / platforms | Architectures & platforms are finalised | Complete | Joey | 4 | 6 | 0 |
| 2 | Create initial master project plan | Master project plan is detailed and complete | Complete | Tyler | 4 | 4 | 0 |
| 3 | Create initial master test plan | Master test plan is detailed and complete | Incomplete | Sanjay | 4 |  | 4 |
| 4 | Initial design for critical core use case | Critical core use case is fully designed | Complete | Isaac | 3 | 3 | 0 |
| 5 | Create tech competency demonstrators | Tech competency demonstrators are functional and use all major technologies | Complete | Tyler | 5 | 6 | 0 |

# Issues

|  |  |  |
| --- | --- | --- |
| Issue | Status | Notes |
|  |  |  |

# Assessment

|  |  |
| --- | --- |
| Assessment target |  |
| Assessment date |  |
| Participants |  |
| Project status |  |