## Risk List
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | WikiWalks
National Center: |  |  | Bathurst CSU
Project Manager Name: |  |  | Joseph Lunt
Project Description: |  |  | WikiWalks is a bush-walking application that crowdsources bush-walk paths from users and aggregates them to create a detailed map of all walking tracks in an area.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
0 | Closed | High | Low | Yellow | WikiWalks will be unable to complete the project initiation or inception stages. | Project failure and subject failure. | Schedule risk, managment risk. | Poor communication between the team members. Poor time management between all or some team members. | One week prior to the task completion date, there are no drafts for any part of the intiation or inception assessments completed. | Mitigate | Regular communication between team members so plans and schedules can be updated in case parts of the project intiaion take longer then expected. | A meeting will be organised where all incomplete tasks are disscused and the members of the group will be able to work on those parts. A follow up meeting will take place 3 days later, and if they are still not complete, the team member will recieve a strike and other members will work together to complete the tasks.
1 | Open | Medium | Medium | Yellow | Individual task in the project takes longer than expected to complete. | Project falls behind schedule and impacts the development time of the whole project. | Schedule risk. | Parts of the project are not completed when they are expected to be. | Task is more difficult than initially perceived, poor communication between team members, unforeseen circumstances prevent team member assigned to task from completing it. | Mitigate | Regular discussions between team members so that if a member is having difficulty with an assigned task, the group is aware of the problem before it is able to cause further delays in the development of the project. A strike against the team member will be enforced if the task was not completed due to poor planning and lack of communication with the group from the member. | All team members are to work together to compete the task before continuing on with the project's development.
2 | Closed | High | Low | Yellow | Google Maps API is too expensive to use for the WikiWalks project. | WikiWalks relies on a map being available in the application. Without one, the application would no longer function as initially intended. Google Maps is the service that WikiWalks intends to use for the maps. | Performance risk, schedule risk, cost risk, strategic risk. | Parts of the project using the Google Maps API take longer than expected to develop, WikiWalks regularly uses the $200 of free credits provided by Google each month. | WIkiWalks uses $200 dollars worth of free credits in a month and is unable to test the project till the month has passed | Mitigate, acceptance | Code review is done before the testing stage is started to ensure that the app accesses Google Maps as little as possible while retaining functionality. | Switch to OpenStreetMaps or another free mapping service.
3 | Open | Medium | Low | Yellow | A member of the WikiWalks development team leaves the project. | Workload is increased for all remaining members. | Schedule risk, operational risk. | A member of the WikiWalks development team is no longer able to work and contribute to the prodject . | 3 strike system being enforced, member leaving for personal reason, member leaving for other factors (e.g. illness). | Acceptance | Team members should try to remain in good spirits and redistribute tasks previously assigned to the leaving member. | For future tasks, split workload amongst the remaining members.
4 | Open | High | Medium | Red | Team is affected by COVID-19 or other illness. | Members may be unable to work on and complete tasks on time. | Schedule risk, outside risk. | Team member(s) become seriously ill and unable to work effectively if at all. | Team member becomes ill and informs the group. | Mitigation | Team members should take precaution to avoid illness, inform the team ASAP if possible, and try to work on what they can. | Other team members take up workload of affected individual and inform Dave and Jim that a team member is currently sick.
5 | Open | Low | Low | Green | Application front-end is unable to be implemented on older Android versions. | Project no longer complies with initial project goals (target API 16, Android 4.1 Jellybean). | Performance risk. | WikiWalks application does not work on Android devices running older versions. | Project requires API features that were yet not implemented by API version 16 and it is too difficult to write a workaround. | Mitigation | Regular testing on devices running old versions, avoiding unnecessary new API features. | Change minimum Andorid API version of WikiWalks to a later version, excluding some older but rarely-used devices.
Risk Map
High
Medium
Low
|  | Low | Medium | High